## Implementation Progress
Feature/Function | Status | Description | Technical Remarks / Implementation Details
Core Evaluation Engine | Implemented | GPT-4o based evaluation of 25-question rubric. | Currently uses single document input (Fact Sheet).
Rubric Question Mapping | Implemented | 25 questions from Tables 3-8 mapped with ABC options. | Weights are applied based on Caltrans standards.
Scoring & Recommendation | Implemented | Weighted composite score calculation and method recommendation. | Supports borderline case detection.
Override Logic | Implemented | 9 document-based override rules (e.g., A1=C blocks DBB). | Transparently logged in recommendation logic.
Excel Export | Implemented | Styled Excel output with results, recommendations, and completeness. | Need to enhance formatting for 'Professional yet Elegant' look.
Multi-Method Scoring (3.1) | Planned | Display scores for all methods (DBB, DB, CMGC, PDB). | Requires update to scoring matrix to generate parallel scores.
Detailed Borderline Analysis (3.2) | In Progress | Pros/Cons for top 2-3 methods when scores are close. | Need to refine the 'influencing factors' extraction logic.
Validation Mode (3.3) | In Progress | Compare AI ratings vs District pre-filled ratings. | Basic extraction exists; flagging mismatches needs UI/Excel integration.
Multi-Document Support (3.6) | Planned | Cross-validation using project reports and additional PDFs. | Requires MCP server or RAG-based multi-doc context handling.
AI vs Expected Analysis (3.7) | Planned | Identify questions causing deviation from human result. | Will require a 'ground truth' input for comparison.
Output Customization (3.10) | Planned | Tailored views for District teams vs Internal reviewers. | Targeting 'Guidance' for Districts and 'Full Comparison' for HQ.

## Feedback Alignment
Requirement | Priority | Current Alignment | Next Steps
3.1 Multi-Method Output | High | Implemented runner-up detection; full list planned. | Will add a 'Comparison Matrix' sheet to the output Excel.
3.2 Borderline Case Handling | High | Basic borderline flag exists. | Developing 'Influencing Factors' summary for top 3 candidates.
3.3 Validation Mode | Very Important | Can extract pre-filled ratings. | Need to implement 'Mismatched Justification' flagging.
3.4 Missing Info Detection | High | Implemented basic detection. | Enhancing to show 'Confidence Impact' per missing field.
3.6 Multi-Document Support | Important | Single-doc focused currently. | Planning integration with local 'Institutional Memory' and Project Reports.
3.9 Target User Alignment | Critical | Focusing on HQ review. | Shifting toward 'Guidance' for Districts to reduce subjectivity.

## Doubts & Clarifications
Area of Concern | Doubt / Question for Clarification | Category
Scoring Weights | Are the current section weights (A=25%, B=20%, etc.) finalized or should they be adjustable by HQ? | Technical
Ground Truth | Do we have a set of 'Expected Results' (Human evaluations) to test the AI vs Expected Analysis? | Data
Multi-Doc Scope | Which 'Additional Supporting Documents' are most critical for validation? (e.g., PSR, PDS, Environmental Reports?) | Process
Override Rules | Are there any new 'Legislative' or 'Policy' overrides not covered in the 9 current rules? | Policy
User Interface | Should 'Validation Mode' be an interactive step (User corrects AI) or a static report comparison? | UX